## Table 1
Name of Work :- Construction of Pipe Distribution Network on Minors along with CADWM from RD 0 to 10000 M on Main Canal of Surewada Lift Irrigation Scheme (Irrigation Potential of 2073 Ha) | [21 empty] | Amount AS PER TENDER | Design | Amount AS PER DESIGN
Name of Item |  |  | Unit | Rate | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender
[5 empty] | Injewada Mr @ RD 120 M |  | Sarpewda Mr @ RD 1110 M |  | Koka Mr 1 @ RD 3240 M |  | Koka Mr 2 @ RD 4645 M |  | Sonkund Mr @ RD 6030 M |  | Palora Mr @ RD 6850 M |  | Kesalwada Mr @ RD 8770 M |  | Dudhara Minor @ RD 1300 m |  | Total |  | Total
[5 empty] | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | 197299.0647 | Qty | 171459.6787 |  | 25619505.1877
Area CCA |  |  | HA | 0 | 124.95 | 149.42 | 47.611 | 58.72 | 454.04 | 530.14 | 52.19 | 77.92 | 164.88 | 221.79 | 493.502 | 612.33 | 133.58 | 162.07 |  | 33.86 | 1470.75 | 114004.6654 | 1812.39 | 99849.3895
HDPE 4 Kg /Cm2
a | 110 | mm | Rmt | 329.2 | 884 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1092 | 359486.4 | 0 | 0 | -359486.4 | -100%
b | 125 | mm | Rmt | 394.9 | 1542 | 0 | 0 | 0 | 2239 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4637 | 1831151.3 | 0 | 0 | -1831151.3 | -100%
c | 140 | mm | Rmt | 487.35 | 327 | 1291.3 | 476 | 1216 | 4731 | 6810 | 447 | 1587 | 3205 | 2527 | 6659 | 7194 | 586 | 1827 |  | 112 | 16431 | 8007647.85 | 22452.3 | 10942128.405 | 2934480.555 | 36.65%
d | 160 | mm | Rmt | 616.95 | 664 | 383.03 | 888 | 0 | 780 | 1458 | 0 | 0 | 944 | 705 | 589 | 919 | 1324 | 866 |  | 297 | 5189 | 3201353.55 | 4331.03 | 2672028.9585 | -529324.5915 | -16.53%
e | 180 | mm | Rmt | 757.95 | 1043 | 610.01 | 465 | 0 | 993 | 1336 | 322 | 0 | 350 | 227 | 529 | 1712 | 109 | 200 |  |  | 3811 | 2888547.45 | 4085.01 | 3096233.3295 | 207685.8795 | 7.19%
f | 200 | mm | Rmt | 922.4 | 836 | 417.52 | 0 | 355 | 0 | 583 | 0 | 94 | 287 | 1250 | 591 | 824 | 169 | 461 |  | 10 | 1883 | 1736879.2 | 3984.52 | 3675321.248 | 1938442.048 | 111.6%
g | 225 | mm | Rmt | 1171 | 264 | 114.35 | 0 | 90 | 484 | 720 | 0 | 0 | 0 | 584 | 1272 | 1360 | 822 | 0 |  | 609 | 2842 | 3327982 | 2868.35 | 3358837.85 | 30855.85 | 0.9272%
h | 250 | mm | Rmt | 1411.8 | 175 | 133.37 | 0 | 472 | 127 | 478 | 219 | 211 | 0 | 236 | 860 | 635 | 144 | 299 |  |  | 1525 | 2152995 | 2464.37 | 3479197.566 | 1326202.566 | 61.6%
i | 280 | mm | Rmt | 1762.25 | 232 | 1008.39 | 313 | 0 | 439 | 388 | 140 | 232 | 235 | 0 | 1040 | 744 | 0 | 237 |  | 371 | 2399 | 4227637.75 | 2609.39 | 4598397.5275 | 370759.7775 | 8.77%
j | 315 | mm | Rmt | 2218.75 | 0 | 0 | 0 | 268 | 348 | 169 | 609 | 168 | 0 | 184 | 1429 | 1640 | 123 | 0 |  | 19 | 2509 | 5566843.75 | 2429 | 5389343.75 | -177500 | -3.189%
k | 355 | mm | Rmt | 2779.4 | 380 | 225.7 | 0 | 40 | 557 | 133 | 875 | 282 | 139 | 383 | 244 | 2215 | 0 | 0 |  |  | 2195 | 6100783 | 3278.7 | 9112818.78 | 3012035.78 | 49.37%
l | 400 | mm | Rmt | 3463.05 | 0 | 0 | 0 | 0 | 905 | 928 | 0 | 843 | 127 | 207 | 550 | 923 | 476 | 0 |  |  | 2058 | 7126956.9 | 2901 | 10046308.05 | 2919351.15 | 40.96%
m | 450 | mm | Rmt | 4297.2 | 0 | 141.94 | 0 | 0 | 0 | 165 | 0 | 0 | 329 | 0 | 1005 | 209 | 0 | 0 |  |  | 1334 | 5732464.8 | 515.94 | 2217097.368 | -3515367.432 | -61.32%
n | 500 | mm | Rmt | 5265.45 | 935 | 517.46 | 0 | 0 | 920 | 259 | 0 | 0 | 0 | 0 | 1527 | 136 | 289 | 933 |  |  | 3671 | 19329466.95 | 1845.46 | 9717177.357 | -9612289.593 | -49.73%
o | 560 | mm | Rmt | 6515.7 | 0 | 1366.33 | 0 | 0 | 963 | 920 | 0 | 0 | 0 | 66 | 0 | 243 | 970 | 174 |  |  | 1933 | 12594848.1 | 2769.33 | 18044123.481 | 5449275.381 | 43.27%
p | 630 | mm | Rmt | 8256.05 | 438 | 106.42 | 0 | 0 | 1173 | 1138 | 0 | 0 | 1531 | 681 | 0 | 516 | 0 | 523 |  |  | 3142 | 25940509.1 | 2964.42 | 24474399.741 | -1466109.359 | -5.652%
q | 710 | mm | Rmt | 10397.35 | 0 | 0 | 0 | 0 | 1537 | 1325 | 0 | 0 | 0 | 638 | 0 | 522 | 615 | 182 |  |  | 2152 | 22375097.2 | 2667 | 27729732.45 | 5354635.25 | 23.93%
r | 800 | mm | Rmt | 12273.5 | 0 | 0 | 0 | 0 | 523 | 1045 | 0 | 0 | 0 | 0 | 539 | 1160 | 0 | 0 |  |  | 1062 | 13034457 | 2205 | 27063067.5 | 14028610.5 | 107.6%
PCCP |  |  |  |  | 7720 | 6315.82 | 2142 | 2441 | 16927 | 17855 | 3468 | 3417 | 7147 | 7688 | 16834 | 20952 | 5627 | 5702 | 0 | 1418 | 59865 | 145535107.3 | 64370.82 | 165616213.3615 | 20081106.0615 | 13.8% | 4505.82 | 7.527%
Item No. 8:- Providing and supplying Prestressed Concrete Cylinder Pipes suitable for sliding ovrelap | [21 empty] | 2431.055 |  | 2572.8461
a | 900 | mm | Rmt | 14199.65 | 0 |  | 0 |  | 716 | 516 | 0 |  | 0 |  | 843 | 565 | 0 |  |  |  | 1559 | 22137254.35 | 1081 | 15349821.65 | -6787432.7 | -30.66%
ITEM NO :1A Excavation for deep trenches for laying rising |  |  | CUM | 158.5 | 11716.26 | 11513.82 | 2671.12 | 3087.36 | 32587.49 | 31295.64 | 4417.09 | 4366.43 | 10505.78 | 10805.03 | 26946.24 | 33610.38 | 9185.58 | 7924.08 |  |  | 98029.56 | 15537685.26 | 102602.74 | 16262534.29 | 724849.03
ITEM NO : 1B EXCAVATION FOR DEEP TRENCHES |  |  | CUM | 647.9 | 1301.81 | 1279.31 | 425.82 | 492.19 | 3620.83 | 3477.29 | 490.79 | 485.15 | 1167.31 | 1200.55 | 2994.03 | 3734.48 | 1464.36 | 1263.25 |  |  | 11464.95 | 7428141.105 | 11932.22 | 7730885.338 | 302744.233
ITEM NO :2 EXCAVATION IN SOFT STARTA |  |  | CUM | 106 | 440.25 | 440.25 | 173.95 | 173.95 | 1079.96 | 1079.96 | 213.11 | 213.11 | 580.13 | 580.13 | 1903.3 | 1903.3 | 383.6 | 383.6 |  |  | 4774.3 | 506075.8 | 4774.3 | 506075.8 | 0
ITEM NO :3 MURUM BEDDING |  |  | CUM | 242.9 | 1232.18 | 1162.29 | 291.06 | 344.91 | 3475.72 | 3357.1 | 548.26 | 541.6 | 1236.26 | 1303.58 | 3144.86 | 3898.66 | 1098.31 | 13766.764 |  |  | 11026.65 | 2678373.285 | 24374.904 | 5920664.1816 | 3242290.8966
ITEM NO : 4 BACKFILLING |  |  | CUM | 47.3 | 7454.7312 | 7315.9052 | 1751.4 | 2011.47 | 19744.8766 | 19011.9461 | 2633.8249 | 2603.267 | 6273.536 | 6488.7399 | 16362.96 | 20244.75 | 5680.3031 | 4931.7525 |  |  | 59901.6318 | 2833347.1853 | 62607.8306 | 2961350.3879 | 128003.2026
ITEM NO :5 RUBBLE SOLLING BELOW |  |  | CUM | 1973 | 39.94 | 39.94 | 20.7 | 20.7 | 98.02 | 98.02 | 24.74 | 24.74 | 58.62 | 58.62 | 171.46 | 171.46 | 41.58 | 41.58 |  |  | 455.06 | 897833.38 | 455.06 | 897833.38 | 0
ITEM NO :6 SAND BEDDING |  |  | CUM | 1276.25 | 364.4 | 343.14 | 98.51 | 111.98 | 1004.2 | 974.54 | 168.75 | 167.08 | 382.84 | 400.93 | 994.92 | 1192.22 | 327.52 | 298.86 |  |  | 3341.14 | 4264129.925 | 3488.75 | 4452517.1875 | 188387.2625
[21 empty] | 0 | 0 | 0 | 0 | 0
ITEM NO 7 | [20 empty] | 0 | 0 | 0 | 0 | 0
| 110 | mm | Rmt | 329.2 | 884 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1092 | 359486.4 | 0 | 0 | -359486.4
| 125 | mm | Rmt | 394.9 | 1542 | 0 | 0 | 0 | 2239 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4637 | 1831151.3 | 0 | 0 | -1831151.3
| 140 | mm | Rmt | 487.35 | 327 | 1291.3 | 476 | 1216 | 4731 | 6810 | 447 | 1587 | 3205 | 2527 | 6659 | 7194 | 586 | 1827 |  |  | 16431 | 8007647.85 | 22452.3 | 10942128.405 | 2934480.555
| 160 | mm | Rmt | 616.95 | 664 | 383.03 | 888 | 0 | 780 | 1458 | 0 | 0 | 944 | 705 | 589 | 919 | 1324 | 866 |  |  | 5189 | 3201353.55 | 4331.03 | 2672028.9585 | -529324.5915
| 180 | mm | Rmt | 757.95 | 1043 | 610.01 | 465 | 0 | 993 | 1336 | 322 | 0 | 350 | 227 | 529 | 1712 | 109 | 200 |  |  | 3811 | 2888547.45 | 4085.01 | 3096233.3295 | 207685.8795
| 200 | mm | Rmt | 922.4 | 836 | 417.52 | 0 | 355 | 0 | 583 | 0 | 94 | 287 | 1250 | 591 | 824 | 169 | 461 |  |  | 1883 | 1736879.2 | 3984.52 | 3675321.248 | 1938442.048
| 225 | mm | Rmt | 1171 | 264 | 114.35 | 0 | 90 | 484 | 720 | 0 | 0 | 0 | 584 | 1272 | 1360 | 822 | 0 |  |  | 2842 | 3327982 | 2868.35 | 3358837.85 | 30855.85
| 250 | mm | Rmt | 1411.8 | 175 | 133.37 | 0 | 472 | 127 | 478 | 219 | 211 | 0 | 236 | 860 | 635 | 144 | 299 |  |  | 1525 | 2152995 | 2464.37 | 3479197.566 | 1326202.566
| 280 | mm | Rmt | 1762.25 | 232 | 1008.39 | 313 | 0 | 439 | 388 | 140 | 232 | 235 | 0 | 1040 | 744 | 0 | 237 |  |  | 2399 | 4227637.75 | 2609.39 | 4598397.5275 | 370759.7775
| 315 | mm | Rmt | 2218.75 | 0 | 0 | 0 | 268 | 348 | 169 | 609 | 168 | 0 | 184 | 1429 | 1640 | 123 | 0 |  |  | 2509 | 5566843.75 | 2429 | 5389343.75 | -177500
| 355 | mm | Rmt | 2779.4 | 380 | 225.7 | 0 | 40 | 557 | 133 | 875 | 282 | 139 | 383 | 244 | 2215 | 0 | 0 |  |  | 2195 | 6100783 | 3278.7 | 9112818.78 | 3012035.78
| 400 | mm | Rmt | 3463.05 | 0 | 0 | 0 | 0 | 905 | 928 | 0 | 843 | 127 | 207 | 550 | 923 | 476 | 0 |  |  | 2058 | 7126956.9 | 2901 | 10046308.05 | 2919351.15
| 450 | mm | Rmt | 4297.2 | 0 | 141.94 | 0 | 0 | 0 | 165 | 0 | 0 | 329 | 0 | 1005 | 209 | 0 | 0 |  |  | 1334 | 5732464.8 | 515.94 | 2217097.368 | -3515367.432
| 500 | mm | Rmt | 5265.45 | 935 | 517.46 | 0 | 0 | 920 | 259 | 0 | 0 | 0 | 0 | 1527 | 136 | 289 | 933 |  |  | 3671 | 19329466.95 | 1845.46 | 9717177.357 | -9612289.593
| 560 | mm | Rmt | 6515.7 | 0 | 1366.33 | 0 | 0 | 963 | 920 | 0 | 0 | 0 | 66 | 0 | 243 | 970 | 174 |  |  | 1933 | 12594848.1 | 2769.33 | 18044123.481 | 5449275.381
| 630 | mm | Rmt | 8256.05 | 438 | 106.42 | 0 | 0 | 1173 | 1138 | 0 | 0 | 1531 | 681 | 0 | 516 | 0 | 523 |  |  | 3142 | 25940509.1 | 2964.42 | 24474399.741 | -1466109.359
| 710 | mm | Rmt | 10397.35 | 0 | 0 | 0 | 0 | 1537 | 1325 | 0 | 0 | 0 | 638 | 0 | 522 | 615 | 182 |  |  | 2152 | 22375097.2 | 2667 | 27729732.45 | 5354635.25
| 800 | mm | Rmt | 12273.5 | 0 | 0 | 0 | 0 | 523 | 1045 | 0 | 0 | 0 | 0 | 539 | 1160 | 0 | 0 |  |  | 1062 | 13034457 | 2205 | 27063067.5 | 14028610.5
Item No. 8:- Providing and supplying Prestressed Concrete Cylinder Pipes suitable for sliding ovrelap | [20 empty] | 0 | 0 | 0 | 0 | 0
a | 900 | mm | Rmt | 14199.65 | 0 |  | 0 |  | 716 | 516 | 0 |  | 0 |  | 843 | 565 | 0 |  |  |  | 1559 | 22137254.35 | 1081 | 15349821.65 | -6787432.7
[21 empty] | 0 | 0 | 0 | 0 | 0
Item No. 9:- Air valves | [20 empty] | 0 | 0 | 0 | 0 | 0
| 50 | mm | No | 11173.65 | 11 | 5 | 5 | 4 | 27 | 25 | 4 | 5 | 14 | 12 | 24 | 29 | 6 | 9 |  |  | 91 | 1016802.15 | 89 | 994454.85 | -22347.3
| 80 | mm | No | 13033.05 | 9 | 8 | 3 | 4 | 7 | 12 | 2 | 2 | 3 | 8 | 14 | 18 | 4 | 4 |  |  | 42 | 547388.1 | 56 | 729850.8 | 182462.7
| 100 | mm | No | 14297.55 | 1 | 2 | 0 | 0 | 6 | 5 | 5 | 4 | 2 | 2 | 11 | 15 | 2 | 1 |  |  | 27 | 386033.85 | 29 | 414628.95 | 28595.1
| 150 | mm | No | 19768.75 | 5 | 5 | 0 | 0 | 10 | 7 | 0 | 0 | 5 | 4 | 5 | 3 | 4 | 5 |  |  | 29 | 573293.75 | 24 | 474450 | -98843.75
| 200 | mm | No | 30815.1 | 0 | 0 | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 5 | 8 | 2 | 0 |  |  | 16 | 493041.6 | 18 | 554671.8 | 61630.2
[21 empty] | 0 | 0 | 0 | 0 | 0
Item No. 10:- Air valves shaft | [20 empty] | 0 | 0 | 0 | 0 | 0
| Upto 180 mm dia pipe line |  | No | 7524 | 11 | 5 | 5 | 4 | 27 | 25 | 4 | 5 | 14 | 12 | 24 | 29 | 6 | 9 |  |  | 91 | 684684 | 89 | 669636 | -15048
| 200 m dia to 400 mm dia pipe line |  | No | 9076.3 | 10 | 10 | 3 | 4 | 13 | 17 | 7 | 6 | 5 | 10 | 25 | 33 | 6 | 5 |  |  | 69 | 626264.7 | 85 | 771485.5 | 145220.8
| 450 m dia to900 mm dia pipe line |  | No | 17283.4 | 5 | 5 | 0 | 0 | 19 | 17 | 0 | 0 | 5 | 4 | 10 | 11 | 6 | 5 |  |  | 45 | 777753 | 42 | 725902.8 | -51850.2
[21 empty] | 0 | 0 | 0 | 0 | 0
Item No. 11:- M15 |  |  |  | 5507.6 | 79.09 | 68.36 | 42.34 | 44.58 | 182.99 | 182.32 | 39.35 | 38.91 | 83.4 | 88.85 | 220.25 | 250.48 | 64.03 | 64.24 |  |  | 711.45 | 3918382.02 | 737.74 | 4063176.824 | 144794.804
Item No. 12:- M20 |  |  |  | 7210.7 | 477.5988 | 419.0248 | 210.24 | 224.94 | 1065.7034 | 1061.3039 | 257.4151 | 254.513 | 524.084 | 555.9501 | 1308.25 | 1479.17 | 390.4669 | 389.8675 |  |  | 4233.7582 | 30528360.077 | 4384.7694 | 31617256.6306 | 1088896.5536
[21 empty] | 0 | 0 | 0 | 0 | 0
Item No.13:-Providing and fixing in position TMT - FE - 500 bar reinforcement of various |  |  | MT | 76604.45 | 26.88 | 23.973 | 14.08 | 14.81 | 56.6 | 56.38 | 15.47 | 15.32 | 29.35 | 30.94 | 68.49 | 77.03 | 22.12 | 22.29 |  |  | 232.99 | 17848070.8055 | 240.743 | 18441985.1063 | 593914.3008
Item No. 14:- Providing, supplying & erecting of CI double flange sluice valve confirming for IS-14846 | [20 empty] | 0 | 0 | 0 | 0 | 0
c | 100 | mm | No. | 11767.5 | 18 | 18 | 7 | 7 | 47 | 47 | 7 | 7 | 19 | 19 | 95 | 95 | 7 | 7 |  |  | 200 | 2353500 | 200 | 2353500 | 0
d | 150 | mm | No. | 16556.95 | 5 | 5 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5 | 13 | 13 | 10 | 10 |  |  | 38 | 629164.1 | 38 | 629164.1 | 0
e | 200 | mm | No. | 25959 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 6 | 6 | 4 | 4 |  |  | 22 | 571098 | 22 | 571098 | 0
f | 250 | mm | No. | 44962.1 | 1 | 1 | 0 | 0 | 3 | 3 | 4 | 4 | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 12 | 539545.2 | 12 | 539545.2 | 0
g | 300 | mm | No. | 59153.75 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 |  |  | 8 | 473230 | 8 | 473230 | 0
h | 350 | mm | No. | 75117.75 | 1 | 1 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 3 | 3 | 1 | 1 |  |  | 13 | 976530.75 | 13 | 976530.75 | 0
i | 400 | mm | No. | 97113.7 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 |  |  | 7 | 679795.9 | 7 | 679795.9 | 0
j | 450 | mm | No. | 126066.2 | 1 | 1 | 0 | 0 | 5 | 5 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 |  |  | 10 | 1260662 | 10 | 1260662 | 0
k | 500 | mm | No. | 144514.9 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 |  |  | 8 | 1156119.2 | 8 | 1156119.2 | 0
l | 600 | mm | No. | 243850.4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 |  |  | 5 | 1219252 | 5 | 1219252 | 0
m | 700 | mm | No. | 388320.75 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4 | 1553283 | 4 | 1553283 | 0
[21 empty] | 0 | 0 | 0 | 0 | 0
Item o. 15:- Providing and fixing M.S. chequerred plate flooring of following thickness supported on |  |  | Sqm | 5104.45 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 |  |  | 39.2 | 200094.44 | 39.2 | 200094.44 | 0
Name of Item |  |  | Unit |  | Injewada Mr @ RD 120 M |  | Sarpewda Mr @ RD 1110 M |  | Koka Mr 1 @ RD 3240 M |  | Koka Mr 2 @ RD 4645 M |  | Sonkund Mr @ RD 6030 M |  | Palora Mr @ RD 6850 M |  | Kesalwada Mr @ RD 8770 M |  |  |  | #VALUE! |  | 0 | 0 | 0
[5 empty] | Qty |  | Qty |  | Qty |  | Qty |  | Qty |  | Qty |  | Qty |  |  |  | #VALUE! |  | 0 | 0 | 0
Item No. 16:- Preparation of upto date digital command maps showing Juridiction of W.U.A. with |  |  | Ha | 110.9 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 |  |  | 1470.75 | 163106.175 | 1835.79 | 203589.111 | 40482.936
Item No. 17:- Preparation and Publication of Benificiers list of WUA etc. Complete |  |  | Ha | 109.55 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 |  |  | 1470.75 | 161120.6625 | 1835.79 | 201110.7945 | 39990.132
Item No. 18:- Providing and making arrangemens for Holding of WUA Election as per instructions of |  |  | Ha | 39.15 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 |  |  | 1470.75 | 57579.8625 | 1835.79 | 71871.1785 | 14291.316
Item No. 19:- Capacity Building of WUA -Arranging and conducting Meetings and Trainings to | [20 empty] | 0 | 0 | 0 | 0 | 0
A) Meeting to be conducted before formation of WUAs , |  |  | meeting | 13342.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 7 | 93400.3 | 7 | 93400.3 | 0
B) Training to be conducted before formation of WUAs , |  |  | training | 25706.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 7 | 179945.5 | 7 | 179945.5 | 0
C) Training to be conducted after formation of |  |  | training | 25706.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 7 | 179945.5 | 7 | 179945.5 | 0
Item No. 20 :-Labour charges for collections of |  |  | ha | 169 | 249.9 | 298.12 | 95.22 | 117.44 | 908.08 | 1059.9 | 104.38 | 155.84 | 329.76 | 444.98 | 987 | 1272.92 | 267.16 | 322.38 |  |  | 2941.5 | 497113.5 | 3671.58 | 620497.02 | 123383.52
Item No. 21:- Full Bore Electromagnetic Flow Meter | [20 empty] | 0 | 0 | 0 | 0 | 0
a | 300 | mm | No | 216024 | 0 | 0 |  | 1 | 0 | 0 | [10 empty] | 0 | 0 | 1 | 216024 | 216024
b | 350 | mm | No | 298787 | 0 | 0 |  |  | 0 | 0 | 1 | 1 | [8 empty] | 1 | 298787 | 1 | 298787 | 0
c | 600 | mm | No | 487378 | 1 | 1 |  |  | 0 | 0 |  |  | 1 | 1 | 0 | [5 empty] | 2 | 974756 | 2 | 974756 | 0
d | 700 | mm | No | 523463 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 |  | 1 |  |  |  | 1 | 523463 | 0 | 0 | -523463
e | 900 | mm | No | 715824 | 0 | 0 |  |  | 1 | 1 |  |  |  |  | 1 | 1 |  |  |  |  | 2 | 1431648 | 2 | 1431648 | 0
| 1200 | mm | No | 523463.49 |  |  | 1 | [10 empty] | 1 |  |  | 1
Item No. 22:- Manufacturing, providing and supplying tapers, "Y" connection with crotch plate, |  |  | kg | 107.75 | 0 | 0 | 2616.85 | 2616.85 | 1130.59 | 1130.59 | 2579.8 | 2579.8 | 0 | 0 | 1106.21 | 1106.21 | 0 | 0 |  |  | 7433.45 | 800954.2375 | 7433.45 | 800954.2375 | 0
Item No. 23:- Hydraulic testing of H. D. P. E. pipe line to specified pressure including cost of all | [20 empty] | 0 | 0 | 0 | 0 | 0
a | 110 | mm | Km | 7818.95 | 0.88 | 0 | 0 | 0 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.09 | 8522.6555 | 0 | 0 | -8522.6555
b | 125 | mm | Km | 8021.3 | 1.54 | 0 | 0 | 0 | 2.24 | 0 | 0.86 | 0.116 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4.64 | 37218.832 | 0.116 | 930.4708 | -36288.3612
c | 140 | mm | Km | 8643.4 | 0.33 | 1.2913 | 0.48 | 1.24 | 4.73 | 6.103 | 0.45 | 0.829 | 3.21 | 2.689 | 6.66 | 7.21 | 0.59 | 1.827 |  |  | 16.45 | 142183.93 | 21.1893 | 183147.5956 | 40963.6656
d | 160 | mm | Km | 8976.3 | 0.66 | 0.17269 | 0.89 | 0 | 0.78 | 1.257 | 0 | 0.642 | 0.94 | 0.766 | 0.59 | 1.36 | 1.32 | 0.866 |  |  | 5.18 | 46497.234 | 5.0637 | 45453.2005 | -1044.0335
e | 180 | mm | Km | 9348.1 | 1.04 | 1.067 | 0.47 | 0.36 | 0.99 | 1.475 | 0.32 | 0 | 0.35 | 0.227 | 0.53 | 2.01 | 0.11 | 0.2 |  |  | 3.81 | 35616.261 | 5.339 | 49909.6929 | 14293.4319
f | 200 | mm | Km | 9758.65 | 0.84 | 0.17085 | 0 | 0 | 0 | 0.372 | 0 | 0.094 | 0.29 | 1.252 | 0.59 | 1.02 | 0.17 | 0.461 |  |  | 1.89 | 18443.8485 | 3.3699 | 32885.1867 | 14441.3382
g | 225 | mm | Km | 10326.55 | 0.26 | 0.11435 | 0 | 0.09 | 0.48 | 1.147 | 0 | 0 | 0 | 0.506 | 1.27 | 1.27 | 0.82 | 0 |  |  | 2.83 | 29224.1365 | 3.1273 | 32294.7361 | 3070.5996
h | 250 | mm | Km | 10955.1 | 0.18 | 0.98567 | 0 | 0.47 | 0.13 | 0.212 | 0.22 | 0.211 | 0 | 0.315 | 0.86 | 0.41 | 0.14 | 0.299 |  |  | 1.53 | 16761.303 | 2.9027 | 31799.0401 | 15037.7371
i | 280 | mm | Km | 11789.45 | 0.23 | 0.15609 | 0.31 | 0.31 | 0.44 | 0.388 | 0.14 | 0.232 | 0.24 | 0.226 | 1.04 | 0.71 | 0 | 0.237 |  |  | 2.4 | 28294.68 | 2.2591 | 26633.4286 | -1661.2514
j | 315 | mm | Km | 13646.9 | 0 | 0 | 0 | 0 | 0.35 | 0.302 | 0.61 | 0.168 | 0 | 0 | 1.43 | 1.4 | 0.12 | 0 |  |  | 2.51 | 34253.719 | 1.87 | 25519.703 | -8734.016
k | 355 | mm | Km | 16566.25 | 0.38 | 0.23 | 0 | 0 | 0.56 | 0.9 | 0.88 | 1.12 | 0.14 | 0.33 | 0.24 | 2.41 | 0 | 0 |  |  | 2.2 | 36445.75 | 4.99 | 82665.5875 | 46219.8375
l | 400 | mm | Km | 20106.25 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0.13 | 0.27 | 0.55 | 0.39 | 0.48 | 0 |  |  | 2.07 | 41619.9375 | 0.66 | 13270.125 | -28349.8125
m | 450 | mm | Km | 23986.05 | 0 | 0.5 | 0 | 0 | 0 | 0.44 | 0 | 0 | 0.33 | 0 | 1.01 | 0.21 | 0 | 0.31 |  |  | 1.34 | 32141.307 | 1.46 | 35019.633 | 2878.326
n | 500 | mm | Km | 28108.55 | 0.94 | 0.16 | 0 | 0 | 0.92 | 0.75 | 0 | 0 | 0 | 0.25 | 1.53 | 0.38 | 0.29 | 0.63 |  |  | 3.68 | 103439.464 | 2.17 | 60995.5535 | -42443.9105
o | 560 | mm | Km | 31320.85 | 0 | 1.37 | 0 | 0 | 0.96 | 0.79 | 0 | 0 | 0 | 0.43 | 0 | 0.25 | 0.97 | 0.17 |  |  | 1.93 | 60449.2405 | 3.01 | 94275.7585 | 33826.518
p | 630 | mm | Km | 35108.4 | 0.44 | 0.11 | 0 | 0 | 1.17 | 0.52 | 0 | 0 | 1.53 | 0.64 | 0 | 0 | 0 | 0.52 |  |  | 3.14 | 110240.376 | 1.79 | 62844.036 | -47396.34
q | 710 | mm | Km | 40353.8 | 0 | 0 | 0 | 0 | 1.54 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.62 | 0.18 |  |  | 2.16 | 87164.208 | 1.83 | 73847.454 | -13316.754
r | 800 | mm | Km | 46997.45 | 0 | 0 | 0 | 0 | 0.52 | 1.05 | 0 | 0 | 0 | 0 | 0.54 | 0.54 | 0 | 0 |  |  | 1.06 | 49817.297 | 1.59 | 74725.9455 | 24908.6485
Item No. 24:- Hydraulic testing of Pre-Stressed Cement Concrete Pipes with rubber ring joints to | [20 empty] | 0 | 0 | 0 | 0 | 0
a | 900 | mm | Km | 55275.6 | 0 | 0 | 0 | 0 | 0.72 | 0.52 | 0 | 0 | 0 | 0 | 0.84 | 0.57 | 0 | 0 |  |  | 1.56 | 86229.936 | 1.09 | 60250.404 | -25979.532
Item No. 25:-Providing, Laying, Jointing, Painting & Identification Numbering to R.C.C. pipe of 1200 | [20 empty] | 0 | 0 | 0 | 0 | 0
T Joint chambers |  |  | Rmt | 10349.45 | 42.5 | 42.5 | 12.5 | 12.5 | 112.5 | 112.5 | 15 | 15 | 20 | 20 | 117.5 | 117.5 | 35 | 35 |  |  | 355 | 3674054.75 | 355 | 3674054.75 | 0
Item No. 26:-Providing B.B. masonry with |  |  | Cum | 6133.55 | 9.52 | 9.522 | 9.52 | 9.52 | 9.52 | 9.522 | 9.52 | 9.522 | 9.52 | 9.522 | 9.52 | 9.52 | 9.52 | 9.522 |  |  | 66.64 | 408739.772 | 66.65 | 408801.1075 | 61.3355
Item No. 27:-Providing internal cement plaster |  |  | Sqm | 273.55 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 |  |  | 283.5 | 77551.425 | 283.5 | 77551.425 | 0
Item No. 28:-Providing sand faced plaster |  |  | Sqm | 642.75 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 |  |  | 308.7 | 198416.925 | 308.7 | 198416.925 | 0
Item No. 29:-Providing and applying two coats of |  |  | Sqm | 79 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 |  |  | 308.7 | 24387.3 | 308.7 | 24387.3 | 0
Item No. 30:-Providing and applying colour-wash of |  |  | Sqm | 10 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 |  |  | 283.5 | 2835 | 283.5 | 2835 | 0
Item No. 31:-Providing and fixing rolling shutter |  |  | Sqm | 4828.9 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 |  |  | 22.05 | 106477.245 | 22.05 | 106477.245 | 0
Item No. 32:-Providing and fixing steel window |  |  | Sqm | 4345 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 |  |  | 16.8 | 72996 | 16.8 | 72996 | 0
Item No. 33:-Providing and fixing mild steel grill work for windows, ventilators, etc. 15 |  |  | Sqm | 1707.1 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 |  |  | 16.8 | 28679.28 | 16.8 | 28679.28 | 0
Item No. 34:- Supplying, installing, testing and commissioning of 1 kWp off grid solar power pack |  |  | Each | 75762 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 7 | 530334 | 7 | 530334 | 0
Item No. 35:-Preparation of detailed construction plan for pipe distribution network system including |  |  | Ha. CCA | 676 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 |  |  | 1470.75 | 994227 | 1835.79 | 1240994.04 | 246767.04
Item No. 36:-Providing assistance in collecting data for preparation of voter list from relevanat |  |  | Ha. CCA | 41.6 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 |  |  | 1470.75 | 61183.2 | 1835.79 | 76368.864 | 15185.664
Item No. 37:-Five year operation maintenance, and repair and of pipe distribution network ,consists of | [21 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
1 year |  | 0.40 % of cost of work |  | 1134362 | [17 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
2 year |  | 0.40 % of cost of work |  | 1134362 | [17 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
3 year |  | 0.40 % of cost of work |  | 1134362 | [17 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
4 year |  | 0.40 % of cost of work |  | 1134362 | [17 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
5 year |  | 0.40 % of cost of work |  | 1134362 | [17 empty] | 1133506.2479 | 0 | 1213874.2462 | 80367.9983
[22 empty] | 290177599.4704 |  | 310751807.0342
20574207.5638

## Sheet1
[5 empty] | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design | Tender | Design |  | Design | Design | Design | Design | Design | Design | Design | Design | Design
Name of Item |  |  | Unit | Rate | Injewada Mr @ RD 120 M |  | Sarpewda Mr @ RD 1110 M |  | Koka Mr 1 @ RD 3240 M |  | Koka Mr 2 @ RD 4645 M |  | Sonkund Mr @ RD 6030 M |  | Palora Mr @ RD 6850 M |  | Kesalwada Mr @ RD 8770 M |  | Dudhara Minor @ RD 1300 m |  | Total | Total | Total | Total |  | Injewada Mr @ RD 120 M | Sarpewda Mr @ RD 1110 M | Koka Mr 1 @ RD 3240 M | Koka Mr 2 @ RD 4645 M | Sonkund Mr @ RD 6030 M | Palora Mr @ RD 6850 M | Kesalwada Mr @ RD 8770 M | Dudhara Minor @ RD 1300 m | Total
[5 empty] | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Qty | Cost | Cost |  | Amount | Amount | Amount | Amount | Amount | Amount | Amount | Amount | Cost
ITEM NO :1A Excavation for deep trenches for laying rising | 0 | 0 | CUM | 158.5 | 11716.26 | 11513.82 | 2671.12 | 3087.36 | 32587.49 | 31295.64 | 4417.09 | 4366.43 | 10505.78 | 10805.03 | 26946.24 | 33610.38 | 9185.58 | 7924.08 | 0 | 0 | 98029.56 | 15537685.26 | 102602.74 | 16262534.29 | 724849.03 | 1824940.47 | 489346.56 | 4960358.94 | 692079.155 | 1712597.255 | 5327245.23 | 1255966.68 |  | 16262534.29 | 16262534.29 | 0
ITEM NO : 1B EXCAVATION FOR DEEP TRENCHES | 0 | 0 | CUM | 647.9 | 1301.81 | 1279.31 | 425.82 | 492.19 | 3620.83 | 3477.29 | 490.79 | 485.15 | 1167.31 | 1200.55 | 2994.03 | 3734.48 | 1464.36 | 1263.25 | 0 | 0 | 11464.95 | 7428141.105 | 11932.22 | 7730885.338 | 302744.233 | 828864.949 | 318889.901 | 2252936.191 | 314328.685 | 777836.345 | 2419569.592 | 818459.675 |  | 7730885.338 | 7730885.338 | 0
ITEM NO :2 EXCAVATION IN SOFT STARTA | 0 | 0 | CUM | 106 | 440.25 | 440.25 | 173.95 | 173.95 | 1079.96 | 1079.96 | 213.11 | 213.11 | 580.13 | 580.13 | 1903.3 | 1903.3 | 383.6 | 383.6 | 0 | 0 | 4774.3 | 506075.8 | 4774.3 | 506075.8 | 0 | 46666.5 | 18438.7 | 114475.76 | 22589.66 | 61493.78 | 201749.8 | 40661.6 |  | 506075.8 | 506075.8 | 0
ITEM NO :3 MURUM BEDDING | 0 | 0 | CUM | 242.9 | 1232.18 | 1162.29 | 291.06 | 344.91 | 3475.72 | 3357.1 | 548.26 | 541.6 | 1236.26 | 1303.58 | 3144.86 | 3898.66 | 1098.31 | 13766.764 | 0 | 0 | 11026.65 | 2678373.285 | 24374.904 | 5920664.1816 | 3242290.8966 | 282320.241 | 83778.639 | 815439.59 | 131554.64 | 316639.582 | 946984.514 | 3343946.9756 |  | 5920664.1816 | 5920664.1816 | 0
ITEM NO : 4 BACKFILLING | 0 | 0 | CUM | 47.3 | 7454.7312 | 7315.9052 | 1751.4 | 2011.47 | 19744.8766 | 19011.9461 | 2633.8249 | 2603.267 | 6273.536 | 6488.7399 | 16362.96 | 20244.75 | 5680.3031 | 4931.7525 | 0 | 0 | 59901.6318 | 2833347.1853 | 62607.8306 | 2961350.3879 | 128003.2026 | 346042.3154 | 95142.531 | 899265.0505 | 123134.5276 | 306917.3962 | 957576.675 | 233271.8923 |  | 2961350.3879 | 2961350.3879 | 0
ITEM NO :5 RUBBLE SOLLING BELOW | 0 | 0 | CUM | 1973 | 39.94 | 39.94 | 20.7 | 20.7 | 98.02 | 98.02 | 24.74 | 24.74 | 58.62 | 58.62 | 171.46 | 171.46 | 41.58 | 41.58 | 0 | 0 | 455.06 | 897833.38 | 455.06 | 897833.38 | 0 | 78801.62 | 40841.1 | 193393.46 | 48812.02 | 115657.26 | 338290.58 | 82037.34 |  | 897833.38 | 897833.38 | 0
ITEM NO :6 SAND BEDDING | 0 | 0 | CUM | 1276.25 | 364.4 | 343.14 | 98.51 | 111.98 | 1004.2 | 974.54 | 168.75 | 167.08 | 382.84 | 400.93 | 994.92 | 1192.22 | 327.52 | 298.86 | 0 | 0 | 3341.14 | 4264129.925 | 3488.75 | 4452517.1875 | 188387.2625 | 437932.425 | 142914.475 | 1243756.675 | 213235.85 | 511686.9125 | 1521570.775 | 381420.075 |  | 4452517.1875 | 4452517.1875 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
ITEM NO 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 110 | mm | Rmt | 329.2 | 884 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1092 | 359486.4 | 0 | 0 | -359486.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 125 | mm | Rmt | 394.9 | 1542 | 0 | 0 | 0 | 2239 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4637 | 1831151.3 | 0 | 0 | -1831151.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 140 | mm | Rmt | 487.35 | 327 | 1291.3 | 476 | 1216 | 4731 | 6810 | 447 | 1587 | 3205 | 2527 | 6659 | 7194 | 586 | 1827 | 0 | 0 | 16431 | 8007647.85 | 22452.3 | 10942128.405 | 2934480.555 | 629315.055 | 592617.6 | 3318853.5 | 773424.45 | 1231533.45 | 3505995.9 | 890388.45 |  | 10942128.405 | 10942128.405 | 0
0 | 160 | mm | Rmt | 616.95 | 664 | 383.03 | 888 | 0 | 780 | 1458 | 0 | 0 | 944 | 705 | 589 | 919 | 1324 | 866 | 0 | 0 | 5189 | 3201353.55 | 4331.03 | 2672028.9585 | -529324.5915 | 236310.3585 | 0 | 899513.1 | 0 | 434949.75 | 566977.05 | 534278.7 |  | 2672028.9585 | 2672028.9585 | 0
0 | 180 | mm | Rmt | 757.95 | 1043 | 610.01 | 465 | 0 | 993 | 1336 | 322 | 0 | 350 | 227 | 529 | 1712 | 109 | 200 | 0 | 0 | 3811 | 2888547.45 | 4085.01 | 3096233.3295 | 207685.8795 | 462357.0795 | 0 | 1012621.2 | 0 | 172054.65 | 1297610.4 | 151590 |  | 3096233.3295 | 3096233.3295 | 0
0 | 200 | mm | Rmt | 922.4 | 836 | 417.52 | 0 | 355 | 0 | 583 | 0 | 94 | 287 | 1250 | 591 | 824 | 169 | 461 | 0 | 0 | 1883 | 1736879.2 | 3984.52 | 3675321.248 | 1938442.048 | 385120.448 | 327452 | 537759.2 | 86705.6 | 1153000 | 760057.6 | 425226.4 |  | 3675321.248 | 3675321.248 | 0
0 | 225 | mm | Rmt | 1171 | 264 | 114.35 | 0 | 90 | 484 | 720 | 0 | 0 | 0 | 584 | 1272 | 1360 | 822 | 0 | 0 | 0 | 2842 | 3327982 | 2868.35 | 3358837.85 | 30855.85 | 133903.85 | 105390 | 843120 | 0 | 683864 | 1592560 | 0 |  | 3358837.85 | 3358837.85 | 0
0 | 250 | mm | Rmt | 1411.8 | 175 | 133.37 | 0 | 472 | 127 | 478 | 219 | 211 | 0 | 236 | 860 | 635 | 144 | 299 | 0 | 0 | 1525 | 2152995 | 2464.37 | 3479197.566 | 1326202.566 | 188291.766 | 666369.6 | 674840.4 | 297889.8 | 333184.8 | 896493 | 422128.2 |  | 3479197.566 | 3479197.566 | 0
0 | 280 | mm | Rmt | 1762.25 | 232 | 1008.39 | 313 | 0 | 439 | 388 | 140 | 232 | 235 | 0 | 1040 | 744 | 0 | 237 | 0 | 0 | 2399 | 4227637.75 | 2609.39 | 4598397.5275 | 370759.7775 | 1777035.2775 | 0 | 683753 | 408842 | 0 | 1311114 | 417653.25 |  | 4598397.5275 | 4598397.5275 | 0
0 | 315 | mm | Rmt | 2218.75 | 0 | 0 | 0 | 268 | 348 | 169 | 609 | 168 | 0 | 184 | 1429 | 1640 | 123 | 0 | 0 | 0 | 2509 | 5566843.75 | 2429 | 5389343.75 | -177500 | 0 | 594625 | 374968.75 | 372750 | 408250 | 3638750 | 0 |  | 5389343.75 | 5389343.75 | 0
0 | 355 | mm | Rmt | 2779.4 | 380 | 225.7 | 0 | 40 | 557 | 133 | 875 | 282 | 139 | 383 | 244 | 2215 | 0 | 0 | 0 | 0 | 2195 | 6100783 | 3278.7 | 9112818.78 | 3012035.78 | 627310.58 | 111176 | 369660.2 | 783790.8 | 1064510.2 | 6156371 | 0 |  | 9112818.78 | 9112818.78 | 0
0 | 400 | mm | Rmt | 3463.05 | 0 | 0 | 0 | 0 | 905 | 928 | 0 | 843 | 127 | 207 | 550 | 923 | 476 | 0 | 0 | 0 | 2058 | 7126956.9 | 2901 | 10046308.05 | 2919351.15 | 0 | 0 | 3213710.4 | 2919351.15 | 716851.35 | 3196395.15 | 0 |  | 10046308.05 | 10046308.05 | 0
0 | 450 | mm | Rmt | 4297.2 | 0 | 141.94 | 0 | 0 | 0 | 165 | 0 | 0 | 329 | 0 | 1005 | 209 | 0 | 0 | 0 | 0 | 1334 | 5732464.8 | 515.94 | 2217097.368 | -3515367.432 | 609944.568 | 0 | 709038 | 0 | 0 | 898114.8 | 0 |  | 2217097.368 | 2217097.368 | 0
0 | 500 | mm | Rmt | 5265.45 | 935 | 517.46 | 0 | 0 | 920 | 259 | 0 | 0 | 0 | 0 | 1527 | 136 | 289 | 933 | 0 | 0 | 3671 | 19329466.95 | 1845.46 | 9717177.357 | -9612289.593 | 2724659.757 | 0 | 1363751.55 | 0 | 0 | 716101.2 | 4912664.85 |  | 9717177.357 | 9717177.357 | 0
0 | 560 | mm | Rmt | 6515.7 | 0 | 1366.33 | 0 | 0 | 963 | 920 | 0 | 0 | 0 | 66 | 0 | 243 | 970 | 174 | 0 | 0 | 1933 | 12594848.1 | 2769.33 | 18044123.481 | 5449275.381 | 8902596.381 | 0 | 5994444 | 0 | 430036.2 | 1583315.1 | 1133731.8 |  | 18044123.481 | 18044123.481 | 0
0 | 630 | mm | Rmt | 8256.05 | 438 | 106.42 | 0 | 0 | 1173 | 1138 | 0 | 0 | 1531 | 681 | 0 | 516 | 0 | 523 | 0 | 0 | 3142 | 25940509.1 | 2964.42 | 24474399.741 | -1466109.359 | 878608.841 | 0 | 9395384.9 | 0 | 5622370.05 | 4260121.8 | 4317914.15 |  | 24474399.741 | 24474399.741 | 0
0 | 710 | mm | Rmt | 10397.35 | 0 | 0 | 0 | 0 | 1537 | 1325 | 0 | 0 | 0 | 638 | 0 | 522 | 615 | 182 | 0 | 0 | 2152 | 22375097.2 | 2667 | 27729732.45 | 5354635.25 | 0 | 0 | 13776488.75 | 0 | 6633509.3 | 5427416.7 | 1892317.7 |  | 27729732.45 | 27729732.45 | 0
0 | 800 | mm | Rmt | 12273.5 | 0 | 0 | 0 | 0 | 523 | 1045 | 0 | 0 | 0 | 0 | 539 | 1160 | 0 | 0 | 0 | 0 | 1062 | 13034457 | 2205 | 27063067.5 | 14028610.5 | 0 | 0 | 12825807.5 | 0 | 0 | 14237260 | 0 |  | 27063067.5 | 27063067.5 | 0
Item No. 8:- Providing and supplying Prestressed Concrete Cylinder Pipes suitable for sliding ovrelap | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
a | 900 | mm | Rmt | 14199.65 | 0 | 0 | 0 | 0 | 716 | 516 | 0 | 0 | 0 | 0 | 843 | 565 | 0 | 0 | 0 | 0 | 1559 | 22137254.35 | 1081 | 15349821.65 | -6787432.7 | 0 | 0 | 7327019.4 | 0 | 0 | 8022802.25 | 0 |  | 15349821.65 | 15349821.65 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item No. 9:- Air valves | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 50 | mm | No | 11173.65 | 11 | 5 | 5 | 4 | 27 | 25 | 4 | 5 | 14 | 12 | 24 | 29 | 6 | 9 | 0 | 0 | 91 | 1016802.15 | 89 | 994454.85 | -22347.3 | 55868.25 | 44694.6 | 279341.25 | 55868.25 | 134083.8 | 324035.85 | 100562.85 |  | 994454.85 | 994454.85 | 0
0 | 80 | mm | No | 13033.05 | 9 | 8 | 3 | 4 | 7 | 12 | 2 | 2 | 3 | 8 | 14 | 18 | 4 | 4 | 0 | 0 | 42 | 547388.1 | 56 | 729850.8 | 182462.7 | 104264.4 | 52132.2 | 156396.6 | 26066.1 | 104264.4 | 234594.9 | 52132.2 |  | 729850.8 | 729850.8 | 0
0 | 100 | mm | No | 14297.55 | 1 | 2 | 0 | 0 | 6 | 5 | 5 | 4 | 2 | 2 | 11 | 15 | 2 | 1 | 0 | 0 | 27 | 386033.85 | 29 | 414628.95 | 28595.1 | 28595.1 | 0 | 71487.75 | 57190.2 | 28595.1 | 214463.25 | 14297.55 |  | 414628.95 | 414628.95 | 0
0 | 150 | mm | No | 19768.75 | 5 | 5 | 0 | 0 | 10 | 7 | 0 | 0 | 5 | 4 | 5 | 3 | 4 | 5 | 0 | 0 | 29 | 573293.75 | 24 | 474450 | -98843.75 | 98843.75 | 0 | 138381.25 | 0 | 79075 | 59306.25 | 98843.75 |  | 474450 | 474450 | 0
0 | 200 | mm | No | 30815.1 | 0 | 0 | 0 | 0 | 9 | 10 | 0 | 0 | 0 | 0 | 5 | 8 | 2 | 0 | 0 | 0 | 16 | 493041.6 | 18 | 554671.8 | 61630.2 | 0 | 0 | 308151 | 0 | 0 | 246520.8 | 0 |  | 554671.8 | 554671.8 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item No. 10:- Air valves shaft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | Upto 180 mm dia pipe line | 0 | No | 7524 | 11 | 5 | 5 | 4 | 27 | 25 | 4 | 5 | 14 | 12 | 24 | 29 | 6 | 9 | 0 | 0 | 91 | 684684 | 89 | 669636 | -15048 | 37620 | 30096 | 188100 | 37620 | 90288 | 218196 | 67716 |  | 669636 | 669636 | 0
0 | 200 m dia to 400 mm dia pipe line | 0 | No | 9076.3 | 10 | 10 | 3 | 4 | 13 | 17 | 7 | 6 | 5 | 10 | 25 | 33 | 6 | 5 | 0 | 0 | 69 | 626264.7 | 85 | 771485.5 | 145220.8 | 90763 | 36305.2 | 154297.1 | 54457.8 | 90763 | 299517.9 | 45381.5 |  | 771485.5 | 771485.5 | 0
0 | 450 m dia to900 mm dia pipe line | 0 | No | 17283.4 | 5 | 5 | 0 | 0 | 19 | 17 | 0 | 0 | 5 | 4 | 10 | 11 | 6 | 5 | 0 | 0 | 45 | 777753 | 42 | 725902.8 | -51850.2 | 86417 | 0 | 293817.8 | 0 | 69133.6 | 190117.4 | 86417 |  | 725902.8 | 725902.8 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item No. 11:- M15 | 0 | 0 | 0 | 5507.6 | 79.09 | 68.36 | 42.34 | 44.58 | 182.99 | 182.32 | 39.35 | 38.91 | 83.4 | 88.85 | 220.25 | 250.48 | 64.03 | 64.24 | 0 | 0 | 711.45 | 3918382.02 | 737.74 | 4063176.824 | 144794.804 | 376499.536 | 245528.808 | 1004145.632 | 214300.716 | 489350.26 | 1379543.648 | 353808.224 |  | 4063176.824 | 4063176.824 | 0
Item No. 12:- M20 | 0 | 0 | 0 | 7210.7 | 477.5988 | 419.0248 | 210.24 | 224.94 | 1065.7034 | 1061.3039 | 257.4151 | 254.513 | 524.084 | 555.9501 | 1308.25 | 1479.17 | 390.4669 | 389.8675 | 0 | 0 | 4233.7582 | 30528360.077 | 4384.7694 | 31617256.6306 | 1088896.5536 | 3021462.2146 | 1621974.858 | 7652744.0434 | 1835217.1198 | 4008789.5456 | 10665851.119 | 2811217.7301 |  | 31617256.6306 | 31617256.6306 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item No.13:-Providing and fixing in position TMT - FE - 500 bar reinforcement of various | 0 | 0 | MT | 76604.45 | 26.88 | 23.973 | 14.08 | 14.81 | 56.6 | 56.38 | 15.47 | 15.32 | 29.35 | 30.94 | 68.49 | 77.03 | 22.12 | 22.29 | 0 | 0 | 232.99 | 17848070.8055 | 240.743 | 18441985.1063 | 593914.3008 | 1836438.4798 | 1134511.9045 | 4318958.891 | 1173580.174 | 2370141.683 | 5900840.7835 | 1707513.1905 |  | 18441985.1063 | 18441985.1063 | 0
Item No. 14:- Providing, supplying & erecting of CI double flange sluice valve confirming for IS-14846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
c | 100 | mm | No. | 11767.5 | 18 | 18 | 7 | 7 | 47 | 47 | 7 | 7 | 19 | 19 | 95 | 95 | 7 | 7 | 0 | 0 | 200 | 2353500 | 200 | 2353500 | 0 | 211815 | 82372.5 | 553072.5 | 82372.5 | 223582.5 | 1117912.5 | 82372.5 |  | 2353500 | 2353500 | 0
d | 150 | mm | No. | 16556.95 | 5 | 5 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5 | 13 | 13 | 10 | 10 | 0 | 0 | 38 | 629164.1 | 38 | 629164.1 | 0 | 82784.75 | 16556.95 | 49670.85 | 16556.95 | 82784.75 | 215240.35 | 165569.5 |  | 629164.1 | 629164.1 | 0
e | 200 | mm | No. | 25959 | 3 | 3 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 6 | 6 | 4 | 4 | 0 | 0 | 22 | 571098 | 22 | 571098 | 0 | 77877 | 51918 | 77877 | 51918 | 51918 | 155754 | 103836 |  | 571098 | 571098 | 0
f | 250 | mm | No. | 44962.1 | 1 | 1 | 0 | 0 | 3 | 3 | 4 | 4 | 1 | 1 | 2 | 2 | 1 | 1 | 0 | 0 | 12 | 539545.2 | 12 | 539545.2 | 0 | 44962.1 | 0 | 134886.3 | 179848.4 | 44962.1 | 89924.2 | 44962.1 |  | 539545.2 | 539545.2 | 0
g | 300 | mm | No. | 59153.75 | 0 | 0 | 1 | 1 | 3 | 3 | 0 | 0 | 0 | 0 | 3 | 3 | 1 | 1 | 0 | 0 | 8 | 473230 | 8 | 473230 | 0 | 0 | 59153.75 | 177461.25 | 0 | 0 | 177461.25 | 59153.75 |  | 473230 | 473230 | 0
h | 350 | mm | No. | 75117.75 | 1 | 1 | 0 | 0 | 4 | 4 | 0 | 0 | 4 | 4 | 3 | 3 | 1 | 1 | 0 | 0 | 13 | 976530.75 | 13 | 976530.75 | 0 | 75117.75 | 0 | 300471 | 0 | 300471 | 225353.25 | 75117.75 |  | 976530.75 | 976530.75 | 0
i | 400 | mm | No. | 97113.7 | 1 | 1 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 7 | 679795.9 | 7 | 679795.9 | 0 | 97113.7 | 0 | 291341.1 | 0 | 97113.7 | 0 | 194227.4 |  | 679795.9 | 679795.9 | 0
j | 450 | mm | No. | 126066.2 | 1 | 1 | 0 | 0 | 5 | 5 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 10 | 1260662 | 10 | 1260662 | 0 | 126066.2 | 0 | 630331 | 0 | 378198.6 | 0 | 126066.2 |  | 1260662 | 1260662 | 0
k | 500 | mm | No. | 144514.9 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 0 | 0 | 8 | 1156119.2 | 8 | 1156119.2 | 0 | 0 | 0 | 722574.5 | 0 | 0 | 144514.9 | 289029.8 |  | 1156119.2 | 1156119.2 | 0
l | 600 | mm | No. | 243850.4 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 5 | 1219252 | 5 | 1219252 | 0 | 0 | 0 | 487700.8 | 0 | 0 | 731551.2 | 0 |  | 1219252 | 1219252 | 0
m | 700 | mm | No. | 388320.75 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1553283 | 4 | 1553283 | 0 | 0 | 0 | 1553283 | 0 | 0 | 0 | 0 |  | 1553283 | 1553283 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item o. 15:- Providing and fixing M.S. chequerred plate flooring of following thickness supported on | 0 | 0 | Sqm | 5104.45 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 5.6 | 0 | 0 | 39.2 | 200094.44 | 39.2 | 200094.44 | 0 | 28584.92 | 28584.92 | 28584.92 | 28584.92 | 28584.92 | 28584.92 | 28584.92 |  | 200094.44 | 200094.44 | 0
Name of Item | 0 | 0 | Unit | 0 | Injewada Mr @ RD 120 M | 0 | Sarpewda Mr @ RD 1110 M | 0 | Koka Mr 1 @ RD 3240 M | 0 | Koka Mr 2 @ RD 4645 M | 0 | Sonkund Mr @ RD 6030 M | 0 | Palora Mr @ RD 6850 M | 0 | Kesalwada Mr @ RD 8770 M | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | Qty | 0 | Qty | 0 | Qty | 0 | Qty | 0 | Qty | 0 | Qty | 0 | Qty | 0 | 0 | 0 | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Item No. 16:- Preparation of upto date digital command maps showing Juridiction of W.U.A. with | 0 | 0 | Ha | 110.9 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 | 0 | 0 | 1470.75 | 163106.175 | 1835.79 | 203589.111 | 40482.936 | 16530.754 | 6512.048 | 58771.455 | 8641.328 | 24674.141 | 70583.414 | 17875.971 |  | 203589.111 | 203589.111 | 0
Item No. 17:- Preparation and Publication of Benificiers list of WUA etc. Complete | 0 | 0 | Ha | 109.55 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 | 0 | 0 | 1470.75 | 161120.6625 | 1835.79 | 201110.7945 | 39990.132 | 16329.523 | 6432.776 | 58056.0225 | 8536.136 | 24373.7795 | 69724.193 | 17658.3645 |  | 201110.7945 | 201110.7945 | 0
Item No. 18:- Providing and making arrangemens for Holding of WUA Election as per instructions of | 0 | 0 | Ha | 39.15 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 | 0 | 0 | 1470.75 | 57579.8625 | 1835.79 | 71871.1785 | 14291.316 | 5835.699 | 2298.888 | 20747.5425 | 3050.568 | 8710.4835 | 24917.409 | 6310.5885 |  | 71871.1785 | 71871.1785 | 0
Item No. 19:- Capacity Building of WUA -Arranging and conducting Meetings and Trainings to | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
A) Meeting to be conducted before formation of WUAs , | 0 | 0 | meeting | 13342.9 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 93400.3 | 7 | 93400.3 | 0 | 13342.9 | 13342.9 | 13342.9 | 13342.9 | 13342.9 | 13342.9 | 13342.9 |  | 93400.3 | 93400.3 | 0
B) Training to be conducted before formation of WUAs , | 0 | 0 | training | 25706.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 179945.5 | 7 | 179945.5 | 0 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 |  | 179945.5 | 179945.5 | 0
C) Training to be conducted after formation of | 0 | 0 | training | 25706.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 179945.5 | 7 | 179945.5 | 0 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 | 25706.5 |  | 179945.5 | 179945.5 | 0
Item No. 20 :-Labour charges for collections of | 0 | 0 | ha | 169 | 249.9 | 298.12 | 95.22 | 117.44 | 908.08 | 1059.9 | 104.38 | 155.84 | 329.76 | 444.98 | 987 | 1272.92 | 267.16 | 322.38 | 0 | 0 | 2941.5 | 497113.5 | 3671.58 | 620497.02 | 123383.52 | 50382.28 | 19847.36 | 179123.1 | 26336.96 | 75201.62 | 215123.48 | 54482.22 |  | 620497.02 | 620497.02 | 0
Item No. 21:- Full Bore Electromagnetic Flow Meter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
a | 300 | mm | No | 216024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 216024 | 216024 | 0 | 216024 | 0 | 0 | 0 | 0 | 0 |  | 216024 | 216024 | 0
b | 350 | mm | No | 298787 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 298787 | 1 | 298787 | 0 | 0 | 0 | 0 | 298787 | 0 | 0 | 0 |  | 298787 | 298787 | 0
c | 600 | mm | No | 487378 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 974756 | 2 | 974756 | 0 | 487378 | 0 | 0 | 0 | 487378 | 0 | 0 |  | 974756 | 974756 | 0
d | 700 | mm | No | 523463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 523463 | 0 | 0 | -523463 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
e | 900 | mm | No | 715824 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 2 | 1431648 | 2 | 1431648 | 0 | 0 | 0 | 715824 | 0 | 0 | 715824 | 0 |  | 1431648 | 1431648 | 0
0 | 1200 | mm | No | 523463.49 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Item No. 22:- Manufacturing, providing and supplying tapers, "Y" connection with crotch plate, | 0 | 0 | kg | 107.75 | 0 | 0 | 2616.85 | 2616.85 | 1130.59 | 1130.59 | 2579.8 | 2579.8 | 0 | 0 | 1106.21 | 1106.21 | 0 | 0 | 0 | 0 | 7433.45 | 800954.2375 | 7433.45 | 800954.2375 | 0 | 0 | 281965.5875 | 121821.0725 | 277973.45 | 0 | 119194.1275 | 0 |  | 800954.2375 | 800954.2375 | 0
Item No. 23:- Hydraulic testing of H. D. P. E. pipe line to specified pressure including cost of all | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
a | 110 | mm | Km | 7818.95 | 0.88 | 0 | 0 | 0 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.09 | 8522.6555 | 0 | 0 | -8522.6555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
b | 125 | mm | Km | 8021.3 | 1.54 | 0 | 0 | 0 | 2.24 | 0 | 0.86 | 0.116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.64 | 37218.832 | 0.116 | 930.4708 | -36288.3612 | 0 | 0 | 0 | 930.4708 | 0 | 0 | 0 |  | 930.4708 | 930.4708 | 0
c | 140 | mm | Km | 8643.4 | 0.33 | 1.2913 | 0.48 | 1.24 | 4.73 | 6.103 | 0.45 | 0.829 | 3.21 | 2.689 | 6.66 | 7.21 | 0.59 | 1.827 | 0 | 0 | 16.45 | 142183.93 | 21.1893 | 183147.5956 | 40963.6656 | 11161.2224 | 10717.816 | 52750.6702 | 7165.3786 | 23242.1026 | 62318.914 | 15791.4918 |  | 183147.5956 | 183147.5956 | 0
d | 160 | mm | Km | 8976.3 | 0.66 | 0.17269 | 0.89 | 0 | 0.78 | 1.257 | 0 | 0.642 | 0.94 | 0.766 | 0.59 | 1.36 | 1.32 | 0.866 | 0 | 0 | 5.18 | 46497.234 | 5.0637 | 45453.2005 | -1044.0335 | 1550.1172 | 0 | 11283.2091 | 5762.7846 | 6875.8458 | 12207.768 | 7773.4758 |  | 45453.2005 | 45453.2005 | 0
e | 180 | mm | Km | 9348.1 | 1.04 | 1.067 | 0.47 | 0.36 | 0.99 | 1.475 | 0.32 | 0 | 0.35 | 0.227 | 0.53 | 2.01 | 0.11 | 0.2 | 0 | 0 | 3.81 | 35616.261 | 5.339 | 49909.6929 | 14293.4319 | 9974.6097 | 3365.316 | 13788.4475 | 0 | 2122.0187 | 18789.681 | 1869.62 |  | 49909.6929 | 49909.6929 | 0
f | 200 | mm | Km | 9758.65 | 0.84 | 0.17085 | 0 | 0 | 0 | 0.372 | 0 | 0.094 | 0.29 | 1.252 | 0.59 | 1.02 | 0.17 | 0.461 | 0 | 0 | 1.89 | 18443.8485 | 3.3699 | 32885.1867 | 14441.3382 | 1667.2654 | 0 | 3630.2178 | 917.3131 | 12217.8298 | 9953.823 | 4498.7377 |  | 32885.1867 | 32885.1867 | 0
g | 225 | mm | Km | 10326.55 | 0.26 | 0.11435 | 0 | 0.09 | 0.48 | 1.147 | 0 | 0 | 0 | 0.506 | 1.27 | 1.27 | 0.82 | 0 | 0 | 0 | 2.83 | 29224.1365 | 3.1273 | 32294.7361 | 3070.5996 | 1180.841 | 929.3895 | 11844.5529 | 0 | 5225.2343 | 13114.7185 | 0 |  | 32294.7361 | 32294.7361 | 0
h | 250 | mm | Km | 10955.1 | 0.18 | 0.98567 | 0 | 0.47 | 0.13 | 0.212 | 0.22 | 0.211 | 0 | 0.315 | 0.86 | 0.41 | 0.14 | 0.299 | 0 | 0 | 1.53 | 16761.303 | 2.9027 | 31799.0401 | 15037.7371 | 10798.1134 | 5148.897 | 2322.4812 | 2311.5261 | 3450.8565 | 4491.591 | 3275.5749 |  | 31799.0401 | 31799.0401 | 0
i | 280 | mm | Km | 11789.45 | 0.23 | 0.15609 | 0.31 | 0.31 | 0.44 | 0.388 | 0.14 | 0.232 | 0.24 | 0.226 | 1.04 | 0.71 | 0 | 0.237 | 0 | 0 | 2.4 | 28294.68 | 2.2591 | 26633.4286 | -1661.2514 | 1840.2153 | 3654.7295 | 4574.3066 | 2735.1524 | 2664.4157 | 8370.5095 | 2794.0997 |  | 26633.4286 | 26633.4286 | 0
j | 315 | mm | Km | 13646.9 | 0 | 0 | 0 | 0 | 0.35 | 0.302 | 0.61 | 0.168 | 0 | 0 | 1.43 | 1.4 | 0.12 | 0 | 0 | 0 | 2.51 | 34253.719 | 1.87 | 25519.703 | -8734.016 | 0 | 0 | 4121.3638 | 2292.6792 | 0 | 19105.66 | 0 |  | 25519.703 | 25519.703 | 0
k | 355 | mm | Km | 16566.25 | 0.38 | 0.23 | 0 | 0 | 0.56 | 0.9 | 0.88 | 1.12 | 0.14 | 0.33 | 0.24 | 2.41 | 0 | 0 | 0 | 0 | 2.2 | 36445.75 | 4.99 | 82665.5875 | 46219.8375 | 3810.2375 | 0 | 14909.625 | 18554.2 | 5466.8625 | 39924.6625 | 0 |  | 82665.5875 | 82665.5875 | 0
l | 400 | mm | Km | 20106.25 | 0 | 0 | 0 | 0 | 0.91 | 0 | 0 | 0 | 0.13 | 0.27 | 0.55 | 0.39 | 0.48 | 0 | 0 | 0 | 2.07 | 41619.9375 | 0.66 | 13270.125 | -28349.8125 | 0 | 0 | 0 | 0 | 5428.6875 | 7841.4375 | 0 |  | 13270.125 | 13270.125 | 0
m | 450 | mm | Km | 23986.05 | 0 | 0.5 | 0 | 0 | 0 | 0.44 | 0 | 0 | 0.33 | 0 | 1.01 | 0.21 | 0 | 0.31 | 0 | 0 | 1.34 | 32141.307 | 1.46 | 35019.633 | 2878.326 | 11993.025 | 0 | 10553.862 | 0 | 0 | 5037.0705 | 7435.6755 |  | 35019.633 | 35019.633 | 0
n | 500 | mm | Km | 28108.55 | 0.94 | 0.16 | 0 | 0 | 0.92 | 0.75 | 0 | 0 | 0 | 0.25 | 1.53 | 0.38 | 0.29 | 0.63 | 0 | 0 | 3.68 | 103439.464 | 2.17 | 60995.5535 | -42443.9105 | 4497.368 | 0 | 21081.4125 | 0 | 7027.1375 | 10681.249 | 17708.3865 |  | 60995.5535 | 60995.5535 | 0
o | 560 | mm | Km | 31320.85 | 0 | 1.37 | 0 | 0 | 0.96 | 0.79 | 0 | 0 | 0 | 0.43 | 0 | 0.25 | 0.97 | 0.17 | 0 | 0 | 1.93 | 60449.2405 | 3.01 | 94275.7585 | 33826.518 | 42909.5645 | 0 | 24743.4715 | 0 | 13467.9655 | 7830.2125 | 5324.5445 |  | 94275.7585 | 94275.7585 | 0
p | 630 | mm | Km | 35108.4 | 0.44 | 0.11 | 0 | 0 | 1.17 | 0.52 | 0 | 0 | 1.53 | 0.64 | 0 | 0 | 0 | 0.52 | 0 | 0 | 3.14 | 110240.376 | 1.79 | 62844.036 | -47396.34 | 3861.924 | 0 | 18256.368 | 0 | 22469.376 | 0 | 18256.368 |  | 62844.036 | 62844.036 | 0
q | 710 | mm | Km | 40353.8 | 0 | 0 | 0 | 0 | 1.54 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0.32 | 0.62 | 0.18 | 0 | 0 | 2.16 | 87164.208 | 1.83 | 73847.454 | -13316.754 | 0 | 0 | 53670.554 | 0 | 0 | 12913.216 | 7263.684 |  | 73847.454 | 73847.454 | 0
r | 800 | mm | Km | 46997.45 | 0 | 0 | 0 | 0 | 0.52 | 1.05 | 0 | 0 | 0 | 0 | 0.54 | 0.54 | 0 | 0 | 0 | 0 | 1.06 | 49817.297 | 1.59 | 74725.9455 | 24908.6485 | 0 | 0 | 49347.3225 | 0 | 0 | 25378.623 | 0 |  | 74725.9455 | 74725.9455 | 0
Item No. 24:- Hydraulic testing of Pre-Stressed Cement Concrete Pipes with rubber ring joints to | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
a | 900 | mm | Km | 55275.6 | 0 | 0 | 0 | 0 | 0.72 | 0.52 | 0 | 0 | 0 | 0 | 0.84 | 0.57 | 0 | 0 | 0 | 0 | 1.56 | 86229.936 | 1.09 | 60250.404 | -25979.532 | 0 | 0 | 28743.312 | 0 | 0 | 31507.092 | 0 |  | 60250.404 | 60250.404 | 0
Item No. 25:-Providing, Laying, Jointing, Painting & Identification Numbering to R.C.C. pipe of 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0
T Joint chambers | 0 | 0 | Rmt | 10349.45 | 42.5 | 42.5 | 12.5 | 12.5 | 112.5 | 112.5 | 15 | 15 | 20 | 20 | 117.5 | 117.5 | 35 | 35 | 0 | 0 | 355 | 3674054.75 | 355 | 3674054.75 | 0 | 439851.625 | 129368.125 | 1164313.125 | 155241.75 | 206989 | 1216060.375 | 362230.75 |  | 3674054.75 | 3674054.75 | 0
Item No. 26:-Providing B.B. masonry with | 0 | 0 | Cum | 6133.55 | 9.52 | 9.522 | 9.52 | 9.52 | 9.52 | 9.522 | 9.52 | 9.522 | 9.52 | 9.522 | 9.52 | 9.52 | 9.52 | 9.522 | 0 | 0 | 66.64 | 408739.772 | 66.65 | 408801.1075 | 61.3355 | 58403.6631 | 58391.396 | 58403.6631 | 58403.6631 | 58403.6631 | 58391.396 | 58403.6631 |  | 408801.1075 | 408801.1075 | 0
Item No. 27:-Providing internal cement plaster | 0 | 0 | Sqm | 273.55 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 0 | 283.5 | 77551.425 | 283.5 | 77551.425 | 0 | 11078.775 | 11078.775 | 11078.775 | 11078.775 | 11078.775 | 11078.775 | 11078.775 |  | 77551.425 | 77551.425 | 0
Item No. 28:-Providing sand faced plaster | 0 | 0 | Sqm | 642.75 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 0 | 0 | 308.7 | 198416.925 | 308.7 | 198416.925 | 0 | 28345.275 | 28345.275 | 28345.275 | 28345.275 | 28345.275 | 28345.275 | 28345.275 |  | 198416.925 | 198416.925 | 0
Item No. 29:-Providing and applying two coats of | 0 | 0 | Sqm | 79 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 44.1 | 0 | 0 | 308.7 | 24387.3 | 308.7 | 24387.3 | 0 | 3483.9 | 3483.9 | 3483.9 | 3483.9 | 3483.9 | 3483.9 | 3483.9 |  | 24387.3 | 24387.3 | 0
Item No. 30:-Providing and applying colour-wash of | 0 | 0 | Sqm | 10 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 40.5 | 0 | 0 | 283.5 | 2835 | 283.5 | 2835 | 0 | 405 | 405 | 405 | 405 | 405 | 405 | 405 |  | 2835 | 2835 | 0
Item No. 31:-Providing and fixing rolling shutter | 0 | 0 | Sqm | 4828.9 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 3.15 | 0 | 0 | 22.05 | 106477.245 | 22.05 | 106477.245 | 0 | 15211.035 | 15211.035 | 15211.035 | 15211.035 | 15211.035 | 15211.035 | 15211.035 |  | 106477.245 | 106477.245 | 0
Item No. 32:-Providing and fixing steel window | 0 | 0 | Sqm | 4345 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 16.8 | 72996 | 16.8 | 72996 | 0 | 10428 | 10428 | 10428 | 10428 | 10428 | 10428 | 10428 |  | 72996 | 72996 | 0
Item No. 33:-Providing and fixing mild steel grill work for windows, ventilators, etc. 15 | 0 | 0 | Sqm | 1707.1 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 0 | 0 | 16.8 | 28679.28 | 16.8 | 28679.28 | 0 | 4097.04 | 4097.04 | 4097.04 | 4097.04 | 4097.04 | 4097.04 | 4097.04 |  | 28679.28 | 28679.28 | 0
Item No. 34:- Supplying, installing, testing and commissioning of 1 kWp off grid solar power pack | 0 | 0 | Each | 75762 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 7 | 530334 | 7 | 530334 | 0 | 75762 | 75762 | 75762 | 75762 | 75762 | 75762 | 75762 |  | 530334 | 530334 | 0
Item No. 35:-Preparation of detailed construction plan for pipe distribution network system including | 0 | 0 | Ha. CCA | 676 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 | 0 | 0 | 1470.75 | 994227 | 1835.79 | 1240994.04 | 246767.04 | 100764.56 | 39694.72 | 358246.2 | 52673.92 | 150403.24 | 430246.96 | 108964.44 |  | 1240994.04 | 1240994.04 | 0
Item No. 36:-Providing assistance in collecting data for preparation of voter list from relevanat | 0 | 0 | Ha. CCA | 41.6 | 124.95 | 149.06 | 47.61 | 58.72 | 454.04 | 529.95 | 52.19 | 77.92 | 164.88 | 222.49 | 493.5 | 636.46 | 133.58 | 161.19 | 0 | 0 | 1470.75 | 61183.2 | 1835.79 | 76368.864 | 15185.664 | 6200.896 | 2442.752 | 22045.92 | 3241.472 | 9255.584 | 26476.736 | 6705.504 |  | 76368.864 | 76368.864 | 0
Item No. 37:-Five year operation maintenance, and repair and of pipe distribution network ,consists of | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
1 year | 0 | 0.40 % of cost of work | 0 | 1134362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
2 year | 0 | 0.40 % of cost of work | 0 | 1134362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
3 year | 0 | 0.40 % of cost of work | 0 | 1134362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
4 year | 0 | 0.40 % of cost of work | 0 | 1134362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
5 year | 0 | 0.40 % of cost of work | 0 | 1134362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1133506.2479 | 0 | 1213874.2462 | 80367.9983 | 117530.4162 | 31964.6901 | 386679.901 | 48596.7686 | 130910.628 | 383397.2113 | 114794.6309 |  | 1213874.2462 | 1213874.2462 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290177599.4704 | 0 | 310751807.0342 | 0 | 30087786.5582 | 8182960.6625 | 98990054.6612 | 12440772.7558 | 33513120.776 | 98149686.0979 | 29387425.5225 | 0 | 310751807.0342 |  | -310751807.0342
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20574207.5638 | 0 | Design: 310751807.0342 |  | -310751807.0342
[26 empty] | Design: 0 |  | 0
289258871
21492936.0342

## COMPARITIVE
MINORS | Tender |  |  | Design |  |  | DIFF
| 1470.75 | CCA | AMOUNT PER CCA | 1812.39 | CCA | AMOUNT PER CCA
Injewada Mr @ RD 120 M | 26797156 | 124.95 | 214463.0332 | 29292474 | 149.42 | 196041.1859 | 2495318
Sarpewda Mr @ RD 1110 M | 7050991 | 47.611 | 148095.8392 | 7920550 | 58.72 | 134886.7507 | 869559
Koka Mr 1 @ RD 3240 M | 100619832 | 454.04 | 221610.0608 | 95180630 | 530.14 | 179538.669 | -5439202
Koka Mr 2 @ RD 4645 M | 11917084 | 52.19 | 228340.3717 | 11890947 | 77.92 | 152604.556 | -26137
Sonkund Mr @ RD 6030 M | 31809007 | 164.88 | 192922.1676 | 30191058 | 221.79 | 136124.5232 | -1617949
Palora Mr @ RD 6850 M | 80359545 | 493.502 | 162835.2975 | 94968184 | 612.33 | 155093.1426 | 14608639
Kesalwada Mr @ RD 8770 M | 30708741 | 133.58 | 229890.2605 | 26500987 | 162.07 | 163515.6846 | -4207754
TOTAL | 289262356 | 1470.753 |  | 295944830 | 1812.39 |  | 6682474 | 196676.7676 | 163289.8162
341.637
| 289259871 |  |  |  | 23.23% |  | 2.31%
2485